|  |  |  | Page 1 of 2 |
| --- | --- | --- | --- |
| SOP-XXX-XXX | Title:Live Event Support SOP |  |  |
| Revision # | New |  |  |
| Department: |  | IT |  |
| Approved By: |  |  |  |
| Approved By: |  |  |  |

### General Purpose

To provide standardized procedures for setting up, monitoring, and troubleshooting kiosks at live events. This ensures consistent service quality, rapid issue resolution, and a smooth client experience.

### Scope

This SOP applies to all Field Operations staff involved in the deployment and support of kiosks for live events, including robots, digital signage, and interactive units.

### Responsibilities

- Field Technicians: Execute setup, testing, client handoff, monitoring, and teardown.

- Project Managers (PM): Approve kiosk placements, relocation requests, and coordinate event logistics.

- IT Team: Provide remote assistance, monitor kiosks via MeshCentral, and troubleshoot connectivity issues.

### 1. Unpacking & Placement

Tools Needed:

- Multi-tool

- Microfiber cloth

- Cable ties

- Floor plan (digital/printed)

Steps:

- Unpack Units

  - Inspect for shipping damage (document any issues)

  - Wipe screens/casing with alcohol wipes

- Position Kiosks

  - Confirm locations with Project Manager using event map

  - Ensure:

    - 1m clearance around interactive units

    - Power outlets within reach

- Robot Specifics

  - Clear movement path

  - Verify charging station placement

### 2. Power-Up & Connectivity

For Online Kiosks:

- Connect keyboard/mouse → Open GUI=> Setting

- Connect to internet: Wi-Fi connect

  - ask for the wifi connect "[SSID]" password "[PWD]"

- Test:

  - Load client URL → Verify no certificate errors

  - Scan booth QR code with your phone

For Digital Signage:

- Let content loop for 5+ minutes → Check for freezing

### 3. Client Confirmation

Handoff Protocol:

- Demonstrate:

  - Power button location

  - QR code functionality (scan test)

- Provide Emergency Contact Card:

  - TECH: [ Dagmawi ]

  - PHONE: [ 437 260 3588 ]

BOOTH LOCATION: [Section #]

### 4. Booth Setup Checklist

Mandatory Items:

- Backdrop installed (wrinkle-free)

- Table with branded tablecloth

- cards stocked

- Business cards displayed

- Spare keyboard/mouse in drawer

Internet Fallback:

- Portable hotspot pre-configured (test speed: fast-cli)

### 5. Ongoing Monitoring

Every 2 Hours:

- Physical Check:

  - Touchscreen responsiveness (draw zigzag with finger)

  - Paper jams (if photo boot printer equipped)

  - Robot battery level (>30%)

- Remote Check via MeshCentral:

  - View live screen → Watch for pop-ups

  - Check resource usage:

Relocation Protocol:

- Get PM approval

- Power down → Move → Re-test:

  - Network reconnect

  - Touch calibration (if interactive)

### 6. Troubleshooting Quick Guide

| Issue | Immediate Action |
| --- | --- |
| Frozen screen | Hold power button 10sec → Reboot |

### 7. Post-Event Shutdown

Data Collection:

wp-stat-export --format=csv > /mnt/usb/analytics.csv

Packing:

- Tag units needing maintenance (red sticker)

- Secure all cables with Velcro straps

Approval:

Field Operations Manager: _______________

Date: ___

## Quick Reference Table

References

List any associated forms to be used along with this SOP - example shipping checklist

| Form # | Title |
| --- | --- |

Revision History

Each time a change is made to the SOP we need to list what we changed and why

| Revision # | Description of Change | Date |
| --- | --- | --- |
| New |  |  |